## Sheet1
Video Title | Video ID | Quiz | Question | Correct | Incorrect 1 | Incorrect 2 | Incorrect 3 | Correct Explanation | Incorrect 1 Explanation | Incorrect 2 Explanation | Incorrect 3 Explanation
Why use Lists? | 01_01 | x | Which of the following is not a benefit of using Microsoft Lists? | store videos files | staying organized | ability to access list from multiple devices | integrates with Microsoft 365 Apps | List is not a storage App. It would not be appropriate to store video files on Lists. | Lists are an excellent tool to use to stay organized | One of the key benefits of Lists is the ability to access lists from multiple devices | It is easy to access Microsoft 365 Apps by clicking the Integrate menu item in Lists
Navigating lists | 01_02 | x | If you want to quickly access one of your lists on the List home page, what could you do? | make it a favorite | tag it as important | rename so it begins with the letter A | sort list by last modified | Favorites are listed at the top of the Lists home page making them easy to access | Lists do not have the ability to tag lists | Lists are not listed alphabetically so renaming to start with the letter A does not show the list first. | Lists sorts Recent lists by the last time accessed, not the last modified.
Creating your first List | 01_03 | x | Which of the following is a List column type? | currency | token | float | rating | Currency is a List column type | Token is not a column type in Lists | Float is not a column type in Lists and typically used in programming languages for decimal numbers. Use the number type in Lists | Rating is not a column type in Lists. Rating is typically a question type.
Creating Lists from Excel | 01_04 | x | A list can be imported from which of the following products? | Excel | Word | PowerPoint | OneNote | If data is stored in Excel, it can be used to create a list | It is not possible to create a list from a Word document | It is not possible to create a list from PowerPoint | It is not possible to create a list from OneNote
Creating Lists from a Template | 01_05 | x | You want to use a template to create a list, but nothing matches exactly what you need. What is the best course of action? Pick the best answer. | pick a template that closely matches your desired list | ask a friend | start from blank | pick a random template | Starting with a template that matches your desired list is an effective way to get a majority of columns. You can delete columns not needed and add columns to create the desired list. |  | Starting from blank is an option, but using a template that closely matches your desired list may save you additional work | Picking a random template is not the best option if there is a template that closely matches your desired lists
Sharing your list | 01_06 | x | Which of the following is not an option when sharing a list? | can share | can edit list | can edit items | can view | Can share is not an option when sharing a list. | Can edit list is a share option that allows users to edit the list | Can edit items is a share option that allows users to edit the items | Can view is a share option that grants the user read only access to the list
Optimizing Lists for Projects | 01_07 | x | Which of the following is not a List view? | bucket | calendar | grid | list | Lists do not have buckets and therefore do not have a bucket view | Calendar is one of the views that can be created in Lists | Grid view is one of the views available by clicking the Edit in grid view in the top left corner | List view is the default view when a list is created
Why use Planner? | 02_01 | x | Which of the following is/are true? | all of these answers | Planner keeps due dates clear | Planner is a great collaboration tool | team members can be assigned tasks in Planner | All three choices are true | One of the key features of Planner is tracking due dates. Have you read the other choices? | Planner is a great tool to collaborate with team members. Have you read the other choices? | One of the key features of Planner is the ability to assign tasks. Have you read the other choices?
Navigating Planner | 02_02 | x | On the Planner hub, how would you see the tasks assigned to you? Select the best answer. | view by Assigned to me | view Recent | view All | view Pinned | You can see the tasks assigned to you by clicking the Assigned to me in the upper left corner | Viewing the Recent plans would allow you to see the plans you visited list but not the tasks assigned to you | Viewing All would allow you to see all the plans you have access to but not the tasks assigned to you | Viewing Pinned would allow you to see the plans you marked as important but not the tasks assigned to you
Creating a plan | 02_03 | x | You can organize tasks in Planner by creating the following: | buckets | playlists | hub | favorites | Buckets are the main way to organize tasks in Planner | Playlists are not available in planner | The Planner hub is the main page to see plans you have access to and create new plans. Tasks cannot be organized in this window | Planner does not have favorites, but you can pin a plan
Managing tasks in Planner | 02_04 | x | Which Planner view would you use to see a summary of tasks by priority, bucket and number of tasks assigned to each member on a single page? | chart | bucket | board | schedule | Chart view nicely organizes tasks by status, bucket, priority, and member | Planner does not have a bucket view | Board view gives you the ability to group by bucket, assigned to and priority but not on a single page | Schedule view would not allow you to see a summary of tasks on a single page
Updating and changing plans | 02_05 | x | Members of your Planner team started receiving email notifications when tasks are assigned or completed. You want to stop these notifications. Which notification setting would you use? | send email to the group when a task is assigned or completed | someone assigns a task to me | a task assigned to me is late, due today, or due in the next 7 days. | email is always sent to the group when a comment is made on a task | By unselecting Send email to the group when a task is assigned or complete, team members will no longer receive email notifications for assigned or completed tasks | Modifying the Someone assigned a task to me notification will not stop team members from receiving email notifications for assigned or completed tasks | Modifying the A tasks assigned to me is late, due today, or due in the next 7 days will not stop team members from receiving email notifications for assigned or completed tasks | Modifying the Send email to the group when a task is assigned or completed will not stop team members from receiving email notifications for assigned or completed tasks
Planner pro tips | 02_06 | x | Which of the following is not an option to add an attachment to a task? | from my playlist | from computer | from Teams files | a link to a URL | It is not possible to add an attachment from your playlist | Adding an attachment from computer allows you to add an attachment from files accessible from your computer | Adding attachments from Teams files allows you to add attachments from files accessible from your Teams account | Adding attachments from a URL allows you to add a URL as an attachment
Why use Project? | 03_01 | x | The critical path shows tasks that if ____ would delay the entire project | delayed | completed | shortened | split | The critical path shows the tasks that when combined take the longest to complete. If any of these tasks are delayed, the end date of the project would take longer so the project would be delayed | If any of the tasks were completed, it would not delay the critical path | If any of the tasks on the critical path are shortened it could make the project end earlier, not delay the project | Splitting tasks on the critical path could shorten the critical path if the tasks could be performed in parallel. It would not delay the project
Navigating your first Project | 03_02 | x | If you want to see all the projects you created, which view would you use? Select the best answer. | created by me | shared with me | recent | favorites | Selecting the Created by me view will show you all the projects you created | Selecting Shared with me view will show you the projects shared with you and not the projects you created | Selecting Recent view may show you the projects you created but may also show projects shared with you. This is not the best answer | The Favorites pane shows the projects you marked as your favorites. It may not show you all the projects you created unless you favorites all the projects you created. This is not the best answer
Creating your first Project | 03_03 | x | To set up the framework for an Agile project, you could create the following for each sprint: | bucket | board | backlog | waterfall | Buckets are the main way to organize tasks in Project. You can use buckets for each sprint in your Agile project | Board is a view the allows you to group tasks several ways like buckets, assigned to, progress, and finish date | The backlog is a list of tasks ordered by priority. Tasks from the backlog would be moved to a sprint | Waterfall is a project management development process that is an alternative to Agile
Building your project plan | 03_04 | x | Which Project view would you use to see tasks in a calendar? | timeline | board | grid | bucket | Timeline view in Project will allow you to see tasks in a calendar | Board is a view the allows you to group tasks by various ways like buckets, assigned to, progress, and finish date but not in a calendar | Grid view allows you to see tasks in sequential order with columns you can select. It does not have a calendar view | Project does not have a bucket view but Board view allows you to group tasks by bucket. You would not be able to see tasks in a calendar when grouped by bucket.
Organizing your work | 03_05 | x | If a task A needs to be complete before a task B can be started, the task B is _____ on task B. Select the best answer. | dependent | delayed | subtask | clone | If task 1 needs to be completed before task 2 can be started, then task 2 is dependent on task 1 | If task 1 needs to be completed before task 2 can be started, then task 2 could be delayed on task 1. This is not the best answer | It is not necessary for task 1 to be completed before tasks 2 if task 2 is a subtask of task 1. | If two tasks are clones of each other, one does not need to be completed before the other
Project pro tips | 03_06 | x | Which view would you use to add another column to a project? | grid | board | timeline | filter | Columns can be added in grid view | Columns cannot be added in board view | Columns cannot be added in timeline view | Columns cannot be added in the filters tab